## AS4_Lst
code | omschrijving | keuzelijst dropdown
S0 | strategic definition | S0_strategic definition
S1 | preparation and brief | S1_preparation and brief | delivery: raming (KKG elementclusters) en programma van eisen
S2 | concept design | S2_concept design | delivery: budget (KKG elementen) en prestatiebestek
S3 | spatial coordination | S3_spatial coordination | delivery: begroting (KKG componenten) en technische bestek
S4 | technical design | S4_technical design
S4A | aanbesteding | S4A_aanbesteding | delivery: MAMO-calculatie en bouwspecificaties
S4B | onderhandeling | S4B_onderhandeling | delivery: nulstaat
S5 | manufacturing & construction | S5_manufacturing & construction
S5A | werkvoorbereiding | S5A_werkvoorbereiding | delivery: financiële prognose voor start der werken / bijwerken financiële prognose / MM-werken
S5B | bouwfase | S5B_bouwfase | delivery: maandelijkse vorderingen o.b.v. DDW
S5C | voorlopige oplevering | S5C_voorlopige oplevering | delivery: staat van bevinding per WGH
S6 | handover | S6_handover
S6A | onderhoudsperiode aannemer | S6A_onderhoudsperiode aannemer
S6B | waarborgperiode aannemer | S6B_waarborgperiode aannemer
S6C | 10-jarige aansprakelijkheid aannemer | S6C_10-jarige aansprakelijkheid aannemer
S7 | use | S7_use
S7A | use - owner | S7A_use - owner
S7B | use - facility manager | S7B_use - facility manager
S7C | use - end user | S7C_use - end user
S8 | end of life = S0

## AS4_SysVar
code | omschrijving | keuzelijst dropdown
[P]#001 | … | [P]#001_…
[P]#002 | … | [P]#002_…
[P]#003 | … | [P]#003_…
… | … | …_…
_
_
_
_

## overzicht normen
RIBA workplan 2020 | RIBA workplan 2013 | BREEAM gebaseerd op RIBA 2011 | NEN 2699 | 2012 DRAFT OmniClass Table 31 - Phases
|  |  |  | Number | Level 1 Title | Definition
|  |  |  | 31-10 00 00 | Inception Phase | Phase for establishing the project vision and means to satisfy the client's business or public service requirement, including site selection, planning considerations, establishment of timeline, method of delivery, budget and which identifies necessary resources (design, legal, financing, insurance, etc.).
|  |  |  | 31-20 00 00 | Conceptualization Phase | Phase to identify the major design ideas in the context of programmatic objectives, facility performance, and activity parameters, to define spaces, and to initiate basic project element considerations.
|  |  |  | 31-30 00 00 | Criteria Definition Phase | Phase to create and refine schematic diagrams of the basic project elements - substructure, shell, interiors, equipment, services, equipment and furnishings, special construction and demolition, and building sitework - that fully establish project spatial and element criteria as the Basis of Design.
|  |  |  | 31-40 00 00 | Design Phase | Phase in which project team establishes means of satisfying project Basis of Design requirements with technical solutions, evaluates alternatives through value analysis or similar processes, and completes initial documentation - Drawings and specified Work Results - for the designed project.
|  |  |  | 31-50 00 00 | Coordination Phase | Phase that bridges the design effort with implementation by integrating constructability and feasibility evaluations of the design in order to further develop spaces, elements, products, and materials necessary for the procurement and execution of the Work irrespective of the method of delivery.
|  |  |  | 31-60 00 00 | Implementation Phase | Phase to implement the coordinated design through construction planning, prefabrication, and field execution characterized by constructor 'means and methods,' and Basis of Construction strategies, controlled by quality assurance and control protocols.
|  |  |  | 31-70 00 00 | Handover Phase | Phase to evaluate the completed Work through testing, inspection, and commissioning activities, including for any Owner-furnished equipment, to ensure that design/performance criteria are met while conforming to applicable codes and standards, and transfer project knowledge from the design/construction team to the Owner/facility management team via demonstrations, training, and documentation.
|  |  |  | 31-80 00 00 | Operations Phase | Phase in which owner or a designated agent occupies, uses, and manages and maintains a facility, which may also include partial or whole facility renovation, repair, reconditioning or remodeling activities as part of the project use lifecycle.
|  |  |  | 31-90 00 00 | Closure Phase | Phase which includes facility closure, preparation for unknown future use, demolition in whole or part, foreclosure, sale, or similar dispensation initiated by the decision that the facility no longer meets the needs of the Owner and cannot be feasibly reconfigured for continued use by that Owner.